## Outline-Milestones
Week | Estimated Deadline | Key Milestone/Task | Related Deliverable | Status | Notes/Dependencies
1 |  | Initial discussion of scope of the project | D2 (Initial Req.) | To Do | Set up communication channels.
2 | 2025-11-14 | Finalize scope of the project | D2 | To Do | Get scope sign-off from mentor/instructor.
3 |  | Begin review of material | D1 | In Progress | Focus on core methodologies for D1.
4 |  | Finish review of material, report | D1 (Draft Complete) | To Do | Finalize D1 text and share draft with team.
5 |  | Propose model/approach based on requirements elicited before | D2 | To Do | Begin drafting the innovation plan for D2.
6 |  | Confirm approach, proposal, begin work | D2 (Final Draft) | To Do | Code environment setup (Repo/Libraries).
7 |  | Research / Initial Code Implementation | D3 | To Do | Setup basic functions for proof of concept.
8 |  | Midpoint Check-in | D3, D4 (Initial Data) | To Do | Present D1 summary and D2 plan progress.
9 |  | Research / Execution | D3, D4 | To Do | Focus on data analysis pipeline.
10 |  | Research / Execution | D4 | To Do | Run initial experiments.
11 |  | Research / Execution | D4 | To Do | Generate first set of graphics.
12 |  | Research / Execution | D4 (Results Draft) | To Do | Ensure all necessary data for D4 is captured.
13 |  | Finalize research, begin project report/presentation | D4 (Final) | To Do | Draft presentation slides (B).
14 |  | Present | Presentation | To Do | Rehearse presentation.
15 |  | Finals | Academic Completion | Complete | Submit all final documents/code repository.

## Research Paper
Week Deadline | Associated Project Milestone | Deliverable Title | Paper Section Covered
Week 4 | Finish review of material, report | Deliverable 1: Literature Review Draft | Background & Related Work
Week 5 | Propose model/approach | Deliverable 2: Proposal & Methodology Draft | Proposed Model & Methods
Week 8 | Midpoint Check-in | Deliverable 3: Initial Data & Experimental Setup | Data/Dataset & Experiment Design
Week 12 | Finish Research Execution | Deliverable 4: Preliminary Results & Discussion Draft | Results & Discussion (Initial)
Week 13 | Finalize research, begin report | Deliverable 5: Introduction, Abstract, & Conclusion Draft | Front Matter & Synthesis