## Outline-Milestones
Week | Estimated Deadline | Key Milestone/Task | Related Deliverable | Primary Owner | Status | Notes/Dependencies
1 |  | Initial discussion of scope of the project | D2 (Initial Req.) | All | To Do | Set up communication channels.
2 | 2025-11-14 | Finalize scope of the project | D2 | B (Proposal Lead) | To Do | Get scope sign-off from mentor/instructor.
3 | 2025-01-31 | Begin review of material | D1 | A (Research Lead) | In Progress | Focus on core methodologies for D1.
4 | 2025-02-07 | Finish review of material, report | D1 (Draft Complete) | A | To Do | Finalize D1 text and share draft with team.
5 | 2025-02-14 | Propose model/approach based on requirements elicited before | D2 | B | To Do | Begin drafting the innovation plan for D2.
6 | 2025-02-21 | Confirm approach, proposal, begin work | D2 (Final Draft) | All | To Do | Code environment setup (Repo/Libraries).
7 | 2025-02-28 | Research / Initial Code Implementation | D3 | C (Code Lead) | To Do | Setup basic functions for proof of concept.
8 | 2025-03-07 | Midpoint Check-in | D3, D4 (Initial Data) | All | To Do | Present D1 summary and D2 plan progress.
9 | 2025-03-14 | Research / Execution | D3, D4 | C, A | To Do | Focus on data analysis pipeline.
10 | 2025-03-21 | Research / Execution | D4 | C, A | To Do | Run initial experiments.
11 | 2025-03-28 | Research / Execution | D4 | C, A | To Do | Generate first set of graphics.
12 | 2025-04-04 | Research / Execution | D4 (Results Draft) | C, A | To Do | Ensure all necessary data for D4 is captured.
13 | 2025-04-11 | Finalize research, begin project report/presentation | D4 (Final) | A, B | To Do | Draft presentation slides (B).
14 | 2025-04-18 | Present | Presentation | All | To Do | Rehearse presentation.
15 | 2025-04-25 | Finals | Academic Completion | N/A | Complete | Submit all final documents/code repository.

## Team Member Contract
Name | Preferred Name | Role in Contract | Email | Net_ID | GitHub acct
Nikola Markovic |  |  | was64@txstate.edu | was64 | https://github.com/NIKOLAKIKI
Sum Sah |  |  | bsl67@txstate.edu | bsl67 | https://github.com/sumit-sah314
Abhinesh Danal |  |  | zbz20@txstate.edu | zbz20 | https://github.com/AbhineshD
All three team members share equal responsibility (33.3% each) across all functional roles, including Research, Coding, and Writing/Reporting. No single member is solely responsible for one domain; rather, expertise will be shared and leveraged to ensure quality and prevent single points of failure.
Area | Shared Responsibility Commitment | Accountability Metric
1. Research & Analysis | Equally contribute to the literature review (Deliverable 1), data sourcing, and final analysis/interpretation of results (Deliverable 4). | Completion of D1 and D4 drafts by deadlines; all members must review and sign off.
2. Code & Implementation | Equally contribute to the development, testing, and debugging of the ML model/proof of concept (Deliverable 3). Ensure code is well-documented and hosted on GitHub. | Equal commit history (within reason) on the GitHub repository; functionality tests pass.
3. Writing & Reporting | Equally contribute to drafting all sections of the final paper (Deliverables 1-5). Maintain consistent voice, clarity, and adherence to academic standards. | Equal distribution of section ownership for drafting (e.g., each member takes one section of the final paper); collective final editing.
4. Time Management | Adhere strictly to all internal deadlines defined in the project schedule (especially Weeks 4, 5, 8, 12, 13). | Weekly status updates (via meeting/chat) where progress against assigned tasks is reported.
5. Communication | Attend all scheduled meetings (minimum weekly check-in) prepared with an update and next steps. Respond to project communications within [Specify time, e.g., 12 hours]. | Attendance record for meetings; responsiveness to group messages.

## Team Meetings - Availability
Name
Nikola Markovic
Sum Sah
Abhinesh Danal

## Research Paper
Week Deadline | Associated Project Milestone | Deliverable Title | Paper Section Covered
Week 4 | Finish review of material, report | Deliverable 1: Literature Review Draft | Background & Related Work
Week 5 | Propose model/approach | Deliverable 2: Proposal & Methodology Draft | Proposed Model & Methods
Week 8 | Midpoint Check-in | Deliverable 3: Initial Data & Experimental Setup | Data/Dataset & Experiment Design
Week 12 | Finish Research Execution | Deliverable 4: Preliminary Results & Discussion Draft | Results & Discussion (Initial)
Week 13 | Finalize research, begin report | Deliverable 5: Introduction, Abstract, & Conclusion Draft | Front Matter & Synthesis